## All departments
NISMCAA 10th Edition (Nigeria Grand Finale) - Action plan: all departments
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026) Everything is planned to finish EARLY: all work done by Sep 30, 2027, hard limit Oct 14, 2027 (4 weeks before).
| Event date (PROPOSED; change here if sponsors move it) | 2027-11-11 | All event-linked dates after Mar 31, 2027 follow this cell. |  |  |  | BEHIND SCHEDULE: NONE Nothing has started yet, so nothing is late. 222 tasks, all Not started.
| Today | 2026-10-26
| Days to the event | 381
| Planned: ALL work done (6 weeks before) | 2027-09-30 | Every build task has a planned finish on or before this day.
| Hard limit: all work finished (4 weeks before) | 2027-10-14 | Planned finish + 2 weeks at the latest. After this: no new tasks.
| Review / rehearsal / contingency window starts | 2027-10-15 | Runs to the day before the event. Review only.
DEPARTMENTS
# | Department | Lead | Tasks | Done | Avg % progress | RED | AMBER | GREEN | GREY | Status | Last planned finish (before the final 4 weeks) | Next open deadline | Behind: task numbers
1 | Office of the Founder | John (Founder) | 16 | 0 | 0% | 0 | 0 | 16 | 0 | On track | 2027-09-30 | 2026-11-06 | -
2 | Programs & Competition | Project Manager | 27 | 0 | 0% | 0 | 0 | 27 | 0 | On track | 2027-09-30 | 2026-12-04 | -
3 | Child Welfare & Safeguarding | To be appointed | 20 | 0 | 0% | 0 | 0 | 20 | 0 | On track | 2027-09-30 | 2026-11-20 | -
4 | Event Operations | To be appointed | 25 | 0 | 0% | 0 | 0 | 25 | 0 | On track | 2027-09-30 | 2026-12-18 | -
5 | Media & Communications | To be appointed | 27 | 0 | 0% | 0 | 0 | 27 | 0 | On track | 2027-09-30 | 2026-11-06 | -
6 | Partnerships & Sponsorship | To be appointed | 28 | 0 | 0% | 0 | 0 | 28 | 0 | On track | 2027-09-30 | 2026-10-29 | -
7 | Academy & Education | To be appointed | 17 | 0 | 0% | 0 | 0 | 17 | 0 | On track | 2027-09-30 | 2026-12-11 | -
8 | Finance & Admin | Executive Director | 21 | 0 | 0% | 0 | 0 | 21 | 0 | On track | 2027-09-30 | 2026-11-27 | -
9 | Technology | To be appointed | 24 | 0 | 0% | 0 | 0 | 24 | 0 | On track | 2027-09-30 | 2026-11-13 | -
10 | International & Diplomacy | Abisade (Legal & Diplomacy Director) | 17 | 0 | 0% | 0 | 0 | 17 | 0 | On track | 2027-09-30 | 2026-11-20 | -
| ALL DEPARTMENTS |  | 222 | 0 | 0% | 0 | 0 | 222 | 0 | On track | 2027-09-30
KEY MILESTONES (new plan around Nov 11, 2027)
# | Milestone |  | Planned date | Days from today | Weeks before the event | Why / what moved (full list on 'Milestone shifts')
1 | Plan approved; legal status and budget work started |  | 2026-12-18 | 53 | 46.9 | Start unchanged (now). Each item now has a finish date: gap list Nov 6, handles Nov 13, venue shortlist Dec 18, 2026.
2 | Sponsor packs sent to the top 15 leads |  | 2026-12-18 | 53 | 46.9 | About 6 weeks later than the old draft, because the funding plan builds the deck first (days 15-45, to Nov 27). The event is 8 months later, so there is no pressure to send earlier than a good deck.
3 | Venue booked in writing |  | 2027-04-30 | 186 | 27.9 | Booked 6.5 months before the event instead of 4. A provisional hold is placed by Mar 12, 2027. The written booking waits for the Mar 31 sponsor-approval gate. Shortlist and quotes come first.
4 | Lagos Ministry endorsement approached |  | 2027-01-29 | 95 | 40.9 | Moved to Dec 2026-Jan 2027 so the sponsor pack and a venue shortlist go with the request.
5 | Theme chosen; 10th Edition announced; registration open |  | 2027-01-11 | 77 | 43.4 | Theme by Dec 11, 2026. Announcement Jan 11, 2027 (10 months before the event) so the date wording is settled first. Registration stays open from Nov 16, 2026 per the old plan.
6 | Rulebook frozen; judges and auditor recruited; scoring tool chosen |  | 2026-12-18 | 53 | 46.9 | Rulebook frozen Dec 18, 2026 (Jury plan). Judge recruitment opens Jan 2027, the course runs Apr-May, certificates Jun 18, auditor by Apr 30, 2027, as in the Jury plan. Press briefing Jan 22.
7 | Sponsor contracts and online campaign |  | 2027-08-31 | 309 | 10.3 | Follow-ups Jan 12; headline and gold sponsors in writing by Jun 30; every agreement by Aug 31, 2027. Online-only activity around Jan 16 and Feb 6, 2027 is kept.
8 | Sponsor-approval gate: date confirmed or changed |  | 2027-03-31 | 156 | 32.1 | New gate, because the date is proposed and subject to sponsor approval. If the date moves, change one cell and every later date moves with it.
9 | Registration and Academic Award nominations close |  | 2027-06-30 | 247 | 19.1 | Closes 4.5 months before the event (old plan: 6 weeks before). Qualifying rounds then have July and August.
10 | Qualifying rounds and scoring dry run |  | 2027-08-27 | 305 | 10.9 | Dry run is the mock round (Jun 25). Qualifying rounds Jul 5-Aug 27, 2027, as the Jury plan says Jul-Sep, pulled to finish early.
11 | Finalists announced; technical rehearsal plan and run sheet; media accreditation |  | 2027-09-24 | 333 | 6.9 | Finalists Sep 10, 2027. Rehearsal plan and run sheet Sep 24. Accreditation closes Sep 30.
12 | Program printing, judge briefing, mock scoring audit |  | 2027-09-30 | 339 | 6 | These were in the last 12 days. They now finish by Sep 30, 2027 (printing, mock audit and rehearsal #1). The judges' final briefing and rehearsal #2 are in the review window, as review only.
13 | ALL WORK DONE (planned) |  | 2027-09-30 | 339 | 6 | John's rule. Every build task finishes by Sep 30, 2027. The hard limit for every task is Oct 14, 2027 (4 weeks before the event).
14 | Hard limit: all work finished |  | 2027-10-14 | 353 | 4 | Event date minus 28 days. After this: no new tasks.
15 | Review, rehearsal and contingency window |  | 2027-10-15 | 354 | 3.9 | Oct 15 to Nov 10, 2027: review, rehearsal and contingency only.
16 | 10th Edition Grand Finale (PROPOSED) |  | 2027-11-11 | 381 | 0 | Replaced by Nov 11, 2027 (John, Oct 26, 2026), a Thursday. Subject to sponsor approval; may still change. The old reasons (elections, Ramadan) no longer apply to this date; the school calendar check is a task in Event Operations.
17 | Results and score summary published; sponsor reports |  | 2027-11-18 | 388 | -1 | Same rule: 7 days after the event.
18 | Impact report and audited event accounts |  | 2028-01-10 | 441 | -8.6 | Same rule: within 60 days (Jan 10, 2028). Planned finish Jan 7, 2028.
Formulas:
Done = [Tasks]-TODAY()

## Timeline
Timeline: how many tasks are active in each department, by month (Oct 2026 - Dec 2027)
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Department | Lead | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
Office of the Founder | John (Founder) | 3 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 1
Programs & Competition | Project Manager | 0 | 2 | 3 | 3 | 4 | 4 | 2 | 2 | 4 | 2 | 4 | 7 | 2 | 6 | 1
Child Welfare & Safeguarding | To be appointed | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 3 | 5 | 4 | 7 | 5 | 2 | 3 | 1
Event Operations | To be appointed | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 5 | 5 | 7 | 7 | 2 | 6 | 1
Media & Communications | To be appointed | 2 | 7 | 6 | 5 | 6 | 4 | 3 | 4 | 3 | 4 | 6 | 8 | 2 | 6 | 1
Partnerships & Sponsorship | To be appointed | 3 | 6 | 7 | 7 | 5 | 6 | 5 | 5 | 5 | 3 | 4 | 3 | 2 | 2 | 1
Academy & Education | To be appointed | 0 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 4 | 4 | 6 | 4 | 2 | 2 | 2
Finance & Admin | Executive Director | 2 | 6 | 4 | 4 | 5 | 5 | 4 | 3 | 3 | 2 | 3 | 4 | 1 | 3 | 3
Technology | To be appointed | 1 | 3 | 2 | 4 | 5 | 6 | 7 | 7 | 8 | 4 | 4 | 4 | 2 | 5 | 1
International & Diplomacy | Abisade (Legal & Diplomacy Director) | 1 | 2 | 2 | 5 | 6 | 4 | 2 | 2 | 3 | 2 | 4 | 4 | 2 | 4 | 1
Final 4 weeks (review only) | [13 empty] | REVIEW | REVIEW
EVENT (proposed) | [14 empty] | EVENT
Sponsor-approval gate (Mar 31, 2027) | [6 empty] | GATE
How to read: each number is how many tasks are active in that department that month (a task is active from its start to its planned finish). Darker blue = busier. Nothing is active after Sep 30, 2027 except review, rehearsal, contingency and after-event work.

## Milestone shifts
Milestone shifts: the old plan (finals Mar 13, 2027) rebuilt around Nov 11, 2027
Source for the old column: NISMCAA_10th_Edition_Plan.docx, section D2 (draft Oct 13, 2026). Its Mar 13, 2027 date is superseded by Nov 11, 2027 (PROPOSED; subject to sponsor approval). Old dates in that plan were suggestions.
# | Old milestone (old plan D2) | Old timing | New milestone | New planned date | Shift | Why it moved
1 | Oct 2026 (now): confirm legal status, FB/IG audit, claim handles, set the budget, shortlist venues | Oct 2026 | Plan approved; legal status and budget work started | 2026-12-18 | Same start | Start unchanged (now). Each item now has a finish date: gap list Nov 6, handles Nov 13, venue shortlist Dec 18, 2026.
2 | Early Nov 2026: send sponsor packs to the top 15 leads | Early Nov 2026 | Sponsor packs sent to the top 15 leads | 2026-12-18 | +7 weeks (about +2 months) | About 6 weeks later than the old draft, because the funding plan builds the deck first (days 15-45, to Nov 27). The event is 8 months later, so there is no pressure to send earlier than a good deck.
3 | Early Nov 2026: book the venue (4 months before the event) | Early Nov 2026 | Venue booked in writing | 2027-04-30 | +26 weeks (about +6 months) | Booked 6.5 months before the event instead of 4. A provisional hold is placed by Mar 12, 2027. The written booking waits for the Mar 31 sponsor-approval gate. Shortlist and quotes come first.
4 | Early Nov 2026: approach the Lagos Ministry for endorsement | Early Nov 2026 | Lagos Ministry endorsement approached | 2027-01-29 | +13 weeks (about +3 months) | Moved to Dec 2026-Jan 2027 so the sponsor pack and a venue shortlist go with the request.
5 | Mid-Nov 2026: choose theme, announce, open school registration | Mid-Nov 2026 | Theme chosen; 10th Edition announced; registration open | 2027-01-11 | +8 weeks (about +2 months) | Theme by Dec 11, 2026. Announcement Jan 11, 2027 (10 months before the event) so the date wording is settled first. Registration stays open from Nov 16, 2026 per the old plan.
6 | Dec 2026: recruit judges and the auditor; choose a digital scoring tool; press briefing | Dec 2026 | Rulebook frozen; judges and auditor recruited; scoring tool chosen | 2026-12-18 | +2 weeks (about +1 months) | Rulebook frozen Dec 18, 2026 (Jury plan). Judge recruitment opens Jan 2027, the course runs Apr-May, certificates Jun 18, auditor by Apr 30, 2027, as in the Jury plan. Press briefing Jan 22.
7 | Jan 2027 (election month): keep campaign going; sponsor follow-ups and contracts | Jan 2027 | Sponsor contracts and online campaign | 2027-08-31 | +33 weeks (about +8 months) | Follow-ups Jan 12; headline and gold sponsors in writing by Jun 30; every agreement by Aug 31, 2027. Online-only activity around Jan 16 and Feb 6, 2027 is kept.
8 | (not in the old plan) | - | Sponsor-approval gate: date confirmed or changed | 2027-03-31 | New | New gate, because the date is proposed and subject to sponsor approval. If the date moves, change one cell and every later date moves with it.
9 | End Jan 2027: registration and nominations close | End Jan 2027 | Registration and Academic Award nominations close | 2027-06-30 | +22 weeks (about +5 months) | Closes 4.5 months before the event (old plan: 6 weeks before). Qualifying rounds then have July and August.
10 | Early-mid Feb 2027: preliminaries and a dry run of scoring | Early-mid Feb 2027 | Qualifying rounds and scoring dry run | 2027-08-27 | +28 weeks (about +7 months) | Dry run is the mock round (Jun 25). Qualifying rounds Jul 5-Aug 27, 2027, as the Jury plan says Jul-Sep, pulled to finish early.
11 | Late Feb 2027: finalists announced, technical rehearsal plan, run sheet, accreditation | Late Feb 2027 | Finalists announced; technical rehearsal plan and run sheet; media accreditation | 2027-09-24 | +30 weeks (about +7 months) | Finalists Sep 10, 2027. Rehearsal plan and run sheet Sep 24. Accreditation closes Sep 30.
12 | 1-12 Mar 2027: final rehearsals, judge briefing, mock scoring audit, program printing | Last 12 days | Program printing, judge briefing, mock scoring audit | 2027-09-30 | +30 weeks (about +7 months) | These were in the last 12 days. They now finish by Sep 30, 2027 (printing, mock audit and rehearsal #1). The judges' final briefing and rehearsal #2 are in the review window, as review only.
13 | (not in the old plan) | - | ALL WORK DONE (planned) | 2027-09-30 | New | John's rule. Every build task finishes by Sep 30, 2027. The hard limit for every task is Oct 14, 2027 (4 weeks before the event).
14 | (not in the old plan) | - | Hard limit: all work finished | 2027-10-14 | New | Event date minus 28 days. After this: no new tasks.
15 | (not in the old plan) | - | Review, rehearsal and contingency window | 2027-10-15 | New | Oct 15 to Nov 10, 2027: review, rehearsal and contingency only.
16 | 13 Mar 2027 (backup Mar 18) | 13 Mar 2027 | 10th Edition Grand Finale (PROPOSED) | 2027-11-11 | +35 weeks (about +8 months) | Replaced by Nov 11, 2027 (John, Oct 26, 2026), a Thursday. Subject to sponsor approval; may still change. The old reasons (elections, Ramadan) no longer apply to this date; the school calendar check is a task in Event Operations.
17 | Within 7 days after | Within 7 days | Results and score summary published; sponsor reports | 2027-11-18 | +35 weeks (about +8 months) | Same rule: 7 days after the event.
18 | Within 60 days after | Within 60 days | Impact report and audited event accounts | 2028-01-10 | +35 weeks (about +8 months) | Same rule: within 60 days (Jan 10, 2028). Planned finish Jan 7, 2028.

## Office of the Founder
Office of the Founder - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Founder & President (Olushola John Adebowale) |  |  | Tasks | 16 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Confirm the eligibility gap list: legal status (CAC), U.S. status and accounts | John (Founder) | 2026-10-26 | 2026-11-06 | 2026-11-20 | Not started | 0% | 11 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 1-14) and 10th Edition plan D2 ('Confirm legal status'). The funding plan wanted this by Oct 28; set to Nov 6 because nothing has started.
2 | Decide the public wording for the date: '2027 - Get ready!' or 'proposed Nov 11, 2027' | John (Founder) | 2026-10-26 | 2026-11-06 | 2026-11-20 | Not started | 0% | 11 | 0% | 0 | GREEN | Source: DECISIONS_CHECKLIST F17 (open ruling). Public pages must say PROPOSED until the date is confirmed.
3 | Approve the Jury System plan, this action plan and the open decisions list | John (Founder) | 2026-10-26 | 2026-11-20 | 2026-12-04 | Not started | 0% | 25 | 0% | 0 | GREEN | Source: Jury System plan section 23 ('Nov 2026: John approves this plan'). Approving this action plan is Suggested.
4 | Choose the 10th Edition theme (options in plan D3) | John (Founder) | 2026-11-02 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: 10th Edition plan D2 ('Mid-Nov 2026: choose the theme') and D3 theme ideas.
5 | Appoint heads for the 7 departments that have no lead yet (after volunteer assessment) | John (Founder) | 2026-11-02 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: Volunteer Roles file ('heads appointed after a few weeks of assessing volunteer contributions'). Dependent: every other department sheet.
6 | Monthly plan review with all department heads (last Monday of each month) | John (Founder) | 2026-11-30 | 2027-09-27 | 2027-10-11 | Not started | 0% | 336 | 0% | 0 | GREEN | Suggested. Use the Meeting Room action plan sheets; any RED or AMBER flag is discussed first.
7 | Record a short Founder video: why NISMCAA turns 10 | John (Founder) | 2026-12-01 | 2027-01-08 | 2027-01-22 | Not started | 0% | 74 | 0% | 0 | GREEN | Source: 10th Edition plan A4 calendar day 5 (founder video). Wording must follow the date decision above.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
8 | Sponsor approval gate: confirm or change the Nov 11, 2027 date using sponsor feedback | John (Founder) | 2027-01-04 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Suggested. If the date changes, change the Event date cell on 'All departments'; every date after Mar 31, 2027 moves with it. Re-check the 4-week rule.
9 | Founder-level meetings with the headline sponsor and key partners | John (Founder) | 2027-01-11 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Funding plan section 7 (sponsor meetings), extended. Suggested timing.
10 | Approve the VIP, patron and dignitary guest list | To be appointed (Protocol & Guest Liaison) | 2027-06-01 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Suggested. Role from Volunteer Roles file (Protocol & Guest Liaison Officer).
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
11 | Send invitations to patrons, VIPs and dignitaries | To be appointed (Correspondence Assistant) | 2027-08-02 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Suggested. Role from Volunteer Roles file (Correspondence & Communications Assistant).
12 | Founder sign-off: every department head confirms all build tasks are done | John (Founder) | 2027-09-20 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: all work done at least 4 weeks before the event. Hard limit Oct 14, 2027.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
13 | Final go / no-go meeting with all department heads | John (Founder) | 2027-10-15 | 2027-10-22 | 2027-10-22 | Not started | 0% | 361 | 0% | 0 | GREEN | Review only. No new tasks may be added after Oct 14, 2027.
14 | Protocol rehearsal for VIPs, patrons and guests (seating, welcome, introductions) | To be appointed (Protocol & Guest Liaison) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Review/rehearsal only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
15 | Thank-you letters to patrons, guests, sponsors and volunteers | John (Founder) | 2027-11-12 | 2027-11-19 | 2027-12-03 | Not started | 0% | 389 | 0% | 0 | GREEN | Suggested. Source: 10th Edition plan D2 (thank-you posts and sponsor reports).
16 | Debrief and lessons-learned report from every department to the Founder | John (Founder) | 2027-11-15 | 2027-12-10 | 2027-12-24 | Not started | 0% | 410 | 0% | 0 | GREEN | Suggested. Mirrors the debrief step in the Academy launch plan (T+1 week).
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Programs & Competition
Programs & Competition - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Project Manager / Secretariat (Chief Judge: Dr Teemac Omotshola Iseli) |  |  | Tasks | 27 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | School registration window open: check each school entry, answer questions | Project Manager | 2026-11-16 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (registration opens mid-Nov 2026). Closing date moved from end Jan 2027 to Jun 30, 2027 - see Milestone shifts. Public date wording follows John's decision.
2 | Draft rulebook v2027.1: rubric, scoring algorithms, vote rules, aid statuses, penalty ranges, tie, rounding and appeal rules | Chief Judge | 2026-11-23 | 2026-12-04 | 2026-12-18 | Not started | 0% | 39 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Dec 2026). Values marked 'John to confirm' in section 24 stay open until John decides.
3 | Approve and freeze rulebook v2027.1 (before any entries are scored) | John (Founder) | 2026-12-07 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: Jury System plan section 23 ('approved and frozen before entries open').
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
4 | Publish the rubric and rules to all schools | Project Manager | 2027-01-04 | 2027-01-29 | 2027-02-12 | Not started | 0% | 95 | 0% | 0 | GREEN | Source: 10th Edition plan D5 (published rubric before the competition).
5 | Jury applications open (agreement tick box, no referees) | Chief Judge | 2027-01-11 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Jan 2027) and Volunteer Roles vetting rules.
6 | Record benchmark performances and reference-score them | Chief Judge | 2027-02-01 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Feb-Mar 2027).
7 | Build the Judges' Course and tests (80% pass; attempt counter) | Chief Judge | 2027-02-01 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Jury System plan sections 7 and 23. Time between attempts: John to confirm.
8 | Judges' Course cohort 1: course, tests and interviews | Chief Judge | 2027-04-12 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Apr-May 2027).
9 | Issue judge certificates; name reserve judges | Chief Judge | 2027-06-01 | 2027-06-18 | 2027-07-02 | Not started | 0% | 235 | 0% | 0 | GREEN | Source: Jury System plan sections 7.3, 11.4 and 23 (Jun 2027).
10 | Mock round using 9th Edition data: first full test of the scoring workflow | Project Manager | 2027-06-01 | 2027-06-25 | 2027-07-09 | Not started | 0% | 242 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Jun 2027) and plan D5 ('dry run'). Joint with Technology.
11 | Judge agreements signed by every appointed judge | Chief Judge | 2027-06-07 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Judge_Agreement document on file. Each judge's terms are set by the organizer (John to supply).
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
12 | Record roster and photos for every entry (mandatory on the online form) | Project Manager | 2027-07-01 | 2027-07-30 | 2027-08-13 | Not started | 0% | 277 | 0% | 0 | GREEN | Source: Jury System plan section 16.6 and the Online Registration Standard draft.
13 | Qualifying rounds in batches (panels added as registrations grow) | Chief Judge | 2027-07-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Jury System plan section 23 (Jul-Sep 2027), pulled earlier to finish by the end of August.
14 | Announce finalists and notify schools | Project Manager | 2027-08-30 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Source: 10th Edition plan D2 ('finalists announced'), moved to Sep 2027.
15 | Collect conflict-of-interest declarations; assign judging panels | Chief Judge | 2027-08-30 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Source: Jury System plan section 23 (was Oct 2027; moved earlier so nothing is left for the final month).
16 | Nominee vote cards issued and public voting opens | Project Manager | 2027-08-30 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Source: Jury System plan sections 12 and 23. Voting then stays open until the finals (running, not a new task). Show/hide leaderboard: John to decide.
17 | Running order of the finals locked (with the 20-30 minute buffer before results) | Project Manager | 2027-09-13 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: 10th Edition plan D5 (buffer time). Suggested date.
18 | Judges' calibration day | Chief Judge | 2027-09-20 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: Jury System plan section 23 (was Oct 2027; moved earlier).
19 | Full rehearsal #1 of the results process: scoring, mock audit, two-person sign-off, sealed envelope | Project Manager | 2027-09-20 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (mock scoring audit) and D5 (two-person sign-off).
20 | Programs sign-off: every competition task complete | Project Manager | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
21 | Judges' final briefing; confirm reserve judges | Chief Judge | 2027-10-18 | 2027-10-29 | 2027-10-29 | Not started | 0% | 368 | 0% | 0 | GREEN | Review only. Source: 10th Edition plan D2 (judge briefing).
22 | Full rehearsal #2 of the results process (review of #1 fixes only) | Project Manager | 2027-10-25 | 2027-11-03 | 2027-11-03 | Not started | 0% | 373 | 0% | 0 | GREEN | Review/rehearsal only. Source: Jury System plan section 23.
23 | Performer and stage rehearsal with Event Operations | Project Manager | 2027-11-01 | 2027-11-08 | 2027-11-08 | Not started | 0% | 378 | 0% | 0 | GREEN | Review/rehearsal only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
24 | Finals day: finals held, voting closes, results released after sign-off | Project Manager | 2027-11-11 | 2027-11-11 | 2027-11-11 | Not started | 0% | 381 | 0% | 0 | GREEN | Source: Jury System plan section 23. The date is PROPOSED.
25 | Per-school reports delivered (each school's appeal window starts on delivery) | Project Manager | 2027-11-11 | 2027-11-12 | 2027-11-26 | Not started | 0% | 382 | 0% | 0 | GREEN | Source: Jury System plan section 23 (within 48 hours).
26 | Publish verified results and score summary | Project Manager | 2027-11-11 | 2027-11-18 | 2027-12-02 | Not started | 0% | 388 | 0% | 0 | GREEN | Source: 10th Edition plan D2 and D5 (within 7 days).
27 | Appeals reviewed and closed; judge consistency reports; records archived | Chief Judge | 2027-11-12 | 2027-12-10 | 2027-12-24 | Not started | 0% | 410 | 0% | 0 | GREEN | Source: Jury System plan sections 20-22 and 23 (Dec 2027). Note: plan D5 said a 72-hour appeal window, the later Jury plan says 7 days. The Jury plan is used here.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Child Welfare & Safeguarding
Child Welfare & Safeguarding - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Designated Safeguarding Lead) |  |  | Tasks | 20 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Review and finalize the Child Protection Policy and photo-consent forms (draft exists) | To be appointed (Safeguarding Lead) | 2026-10-26 | 2026-11-20 | 2026-12-04 | Not started | 0% | 25 | 0% | 0 | GREEN | Source: Funding plan section 7 (draft safeguarding policy and consent forms); draft on file: NISMCAA_Child_Protection_Policy_DRAFT.
2 | Appoint the Designated Safeguarding Lead (DSL) | John (Founder) | 2026-11-02 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: Volunteer Roles file (all child-welfare roles report to the DSL).
3 | Founder approves the Child Protection Policy | John (Founder) | 2026-11-16 | 2026-12-04 | 2026-12-18 | Not started | 0% | 39 | 0% | 0 | GREEN | Suggested. Funders and schools ask for this first.
4 | Finalize photo and media consent forms for schools and parents | To be appointed (DSL) | 2026-12-07 | 2027-01-29 | 2027-02-12 | Not started | 0% | 95 | 0% | 0 | GREEN | Source: 10th Edition plan A1 (written consent before posting minors).
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
5 | Finalize volunteer vetting steps: course, 80% test, 9/10 child-protection score, ID, background check for extra-check roles | To be appointed (DSL) | 2027-01-04 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Volunteer Roles file (vetting rules).
6 | Accessibility and special-needs plan for entrants and audience | To be appointed (Special Needs Support) | 2027-03-01 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Funding plan section 6 (accessibility plan is a gap). Registration form already asks for special-needs details.
7 | Recruit and vet child-facing volunteers (welfare officers, chaperones, reunion point, special-needs support) | To be appointed (DSL) | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file.
8 | Write the lost-child and reunion procedure (code word, reunion point, release only to authorized adults) | To be appointed (DSL) | 2027-05-03 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Suggested. Adapted from the lost-child steps in the Academy launch plan.
9 | Chaperone ratios and group-supervision plan; arrival and departure plan with Event Operations | To be appointed (DSL) | 2027-06-01 | 2027-08-13 | 2027-08-27 | Not started | 0% | 291 | 0% | 0 | GREEN | Suggested.
10 | Arrange first aid cover and an incident log | To be appointed (First Aid & Wellbeing) | 2027-06-01 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file (First Aid & Wellbeing). Suggested timing.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
11 | Collect school and parent consent for all performers; share consent lists with Media | To be appointed (DSL) | 2027-07-05 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested. Media posts only consented children.
12 | Safeguarding training for all child-facing volunteers | To be appointed (DSL) | 2027-08-02 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Source: Academy launch plan uses the same training step. Suggested timing.
13 | All child-facing volunteers cleared and issued IDs | To be appointed (DSL) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: Volunteer Roles file (no ID until management approval).
14 | Incident reporting and escalation process; safeguarding briefing pack | To be appointed (DSL) | 2027-08-16 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Suggested.
15 | Safeguarding sign-off: every task complete | To be appointed (DSL) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
16 | Briefing for all child-facing volunteers (review of plan only) | To be appointed (DSL) | 2027-10-18 | 2027-10-29 | 2027-10-29 | Not started | 0% | 368 | 0% | 0 | GREEN | Review only. Suggested.
17 | Child-safety walk-through of the venue with Event Operations (exits, toilets, reunion point, quiet room) | To be appointed (DSL) | 2027-10-25 | 2027-11-03 | 2027-11-03 | Not started | 0% | 373 | 0% | 0 | GREEN | Review only. Suggested.
18 | Table-top drill: lost child and medical emergency | To be appointed (DSL) | 2027-11-01 | 2027-11-08 | 2027-11-08 | Not started | 0% | 378 | 0% | 0 | GREEN | Contingency only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
19 | Review the incident log and report to the Founder | To be appointed (DSL) | 2027-11-12 | 2027-11-26 | 2027-12-10 | Not started | 0% | 396 | 0% | 0 | GREEN | Suggested.
20 | Archive consent records and apply the data-retention rule | To be appointed (DSL) | 2027-12-01 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Source: Jury System plan section 21. Retention period (2 or 3 years): John to confirm.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Event Operations
Event Operations - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Event Operations Manager) |  |  | Tasks | 25 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Venue shortlist and requirements: capacity, stage, backstage, rehearsal rooms, AV, power backup, access, parking | To be appointed (Event Operations Manager) | 2026-11-09 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (shortlist venues) and D4 options: UNILAG auditoria, MUSON Centre, NUT Pavilion, Adeyemi-Bero Auditorium, hotel/events center. JK Ade Ajayi Auditorium is also discussed (confirmed only after a written booking).
2 | Check the Lagos school calendar and public holidays for Thursday Nov 11, 2027 | To be appointed (Event Operations Manager) | 2026-12-01 | 2027-01-15 | 2027-01-29 | Not started | 0% | 81 | 0% | 0 | GREEN | Source: 10th Edition plan D1. Nov 11, 2027 is a Thursday. The 2027/28 calendar may not be published yet; re-check below.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
3 | Request quotes and availability for Nov 11, 2027 and a backup date from at least 3 venues | To be appointed (Event Operations Manager) | 2027-01-11 | 2027-02-12 | 2027-02-26 | Not started | 0% | 109 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (at least 3 quotes). Backup date: John to supply.
4 | Provisional venue hold (no commitment before the sponsor approval gate) | To be appointed (Event Operations Manager) | 2027-02-15 | 2027-03-12 | 2027-03-26 | Not started | 0% | 137 | 0% | 0 | GREEN | Suggested.
5 | Confirm the venue booking in writing after the date gate | To be appointed (Event Operations Manager) | 2027-04-01 | 2027-04-30 | 2027-05-14 | Not started | 0% | 186 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (book the venue; originally early Nov 2026). Do not call the venue confirmed until a written booking exists.
6 | Recruit and vet Event Operations volunteers: front desk, hospitality, sanitation, security, logistics, ushering | To be appointed (Event Operations Manager) | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file.
7 | Site visit with Technology, Child Welfare and Media | To be appointed (Event Operations Manager) | 2027-05-03 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Suggested.
8 | Re-check the Lagos school calendar once the 2027/28 dates are published | To be appointed (Event Operations Manager) | 2027-05-03 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Suggested.
9 | Insurance, permits, venue rules and the venue emergency plan | To be appointed (Event Operations Manager) | 2027-05-03 | 2027-07-30 | 2027-08-13 | Not started | 0% | 277 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (security, first aid, insurance lines).
10 | Door and ticket procedure agreed: unique ticket code, one use, scanned at entry | To be appointed (Event Operations Manager) | 2027-06-01 | 2027-08-13 | 2027-08-27 | Not started | 0% | 291 | 0% | 0 | GREEN | Source: NISMCAA website knowledge (unique ticket code recorded at admission). The payment link is on hold (see Technology).
11 | School arrival and departure plan; equipment transport and logistics | To be appointed (Event Operations Manager) | 2027-06-01 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file (Logistics & Transport). Suggested timing.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
12 | Hospitality plan: green room, refreshments for judges, guests and performers | To be appointed (Event Operations Manager) | 2027-07-05 | 2027-09-03 | 2027-09-17 | Not started | 0% | 312 | 0% | 0 | GREEN | Source: Volunteer Roles file (Hospitality).
13 | Security and crowd-safety plan agreed with the venue | To be appointed (Event Operations Manager) | 2027-08-02 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Source: Volunteer Roles file (Security & Crowd Safety).
14 | Check-in plan: badges, wristbands and check-in lists built from the rosters | To be appointed (Event Operations Manager) | 2027-08-02 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Source: Volunteer Roles file (Registration & Front Desk).
15 | Run sheet for finals day (includes the buffer before results are announced) | To be appointed (Event Operations Manager) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (run sheet) and D5 (20-30 minute buffer).
16 | Technical rehearsal plan, floor plan and signage plan | To be appointed (Event Operations Manager) | 2027-09-06 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (technical rehearsal plan).
17 | Contingency plan: power or internet failure, weather and traffic, volunteer no-shows | To be appointed (Event Operations Manager) | 2027-09-06 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: Jury System plan section 15.1 (emergency backup). Suggested for the rest.
18 | Event Operations sign-off: every task complete | To be appointed (Event Operations Manager) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
19 | Venue walk-through with all department leads | To be appointed (Event Operations Manager) | 2027-10-18 | 2027-10-22 | 2027-10-22 | Not started | 0% | 361 | 0% | 0 | GREEN | Review only.
20 | Volunteer briefing; roster and ID check | To be appointed (Event Operations Manager) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Review only.
21 | Full dress rehearsal on site: stage, sound, lights, performer flow | To be appointed (Event Operations Manager) | 2027-11-01 | 2027-11-08 | 2027-11-08 | Not started | 0% | 378 | 0% | 0 | GREEN | Rehearsal only. Venue access permitting.
22 | Final contingency check: weather, transport, power, volunteer cover | To be appointed (Event Operations Manager) | 2027-11-08 | 2027-11-10 | 2027-11-10 | Not started | 0% | 380 | 0% | 0 | GREEN | Contingency only.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
23 | Event day operations | To be appointed (Event Operations Manager) | 2027-11-11 | 2027-11-11 | 2027-11-11 | Not started | 0% | 381 | 0% | 0 | GREEN | The date is PROPOSED.
24 | Venue hand-back, equipment return, lost property | To be appointed (Event Operations Manager) | 2027-11-12 | 2027-11-19 | 2027-12-03 | Not started | 0% | 389 | 0% | 0 | GREEN | Suggested.
25 | Volunteer debrief and feedback summary | To be appointed (Event Operations Manager) | 2027-11-15 | 2027-12-03 | 2027-12-17 | Not started | 0% | 403 | 0% | 0 | GREEN | Suggested.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Media & Communications
Media & Communications - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Media Lead) |  |  | Tasks | 27 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Audit the Facebook and Instagram accounts: handle, bio, link, category, Business Suite with 2+ admins and 2FA, baseline numbers | To be appointed (Social Media & Content) | 2026-10-26 | 2026-11-06 | 2026-11-20 | Not started | 0% | 11 | 0% | 0 | GREEN | Source: 10th Edition plan A1 (audit, about 2 hours) and D2 (Oct 2026).
2 | Claim the same handle on TikTok, YouTube, LinkedIn, X and a WhatsApp Channel (first choice @nismcaa) | To be appointed (Social Media & Content) | 2026-10-26 | 2026-11-13 | 2026-11-27 | Not started | 0% | 18 | 0% | 0 | GREEN | Source: 10th Edition plan A2 and D2 (Oct 2026). Use the organization email, never a personal one.
3 | Set up the TikTok and YouTube channels (brand account, 2 managers, banner, trailer) | To be appointed (Social Media & Content) | 2026-11-09 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: 10th Edition plan A2.
4 | Agree social media safeguarding rules with Child Welfare (consent before posting minors, comment filters) | To be appointed (Media Lead) | 2026-11-16 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: 10th Edition plan A1.
5 | Brand pack: logo with a 10th-edition badge, Facebook cover, highlights, press kit | To be appointed (Media Lead) | 2026-11-16 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: 10th Edition plan A1.
6 | Collect archive photos and videos of editions 1-9 (with consent) for playlists and the sponsor deck | To be appointed (Photography & Video) | 2026-11-16 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Funding plan section 7 (gather the archive); plan A2 (past performances).
7 | Monthly numbers report: followers, reach, engagement against the baseline | To be appointed (Social Media & Content) | 2026-11-30 | 2027-09-27 | 2027-10-11 | Not started | 0% | 336 | 0% | 0 | GREEN | Source: 10th Edition plan A1 (baseline numbers). Running task.
8 | Press release and press briefing for the announcement | To be appointed (Press & PR) | 2026-12-14 | 2027-01-22 | 2027-02-05 | Not started | 0% | 88 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (Dec 2026 press briefing) and press release template. Keep amounts and scoring details out of public copy until they are final.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
9 | Update the website: key dates, 'How we judge' page, press page (with Technology) | To be appointed (Media Lead) | 2027-01-04 | 2027-02-26 | 2027-03-12 | Not started | 0% | 123 | 0% | 0 | GREEN | Source: 10th Edition plan D5 (website page on judging).
10 | Announce the 10th Edition and run the 30-day launch calendar (online only) | To be appointed (Media Lead) | 2027-01-11 | 2027-02-09 | 2027-02-23 | Not started | 0% | 106 | 0% | 0 | GREEN | Source: 10th Edition plan A4 (day 1 = announcement). Avoid physical events around Jan 16 and Feb 6, 2027 (election dates in the source). Wording follows John's date decision.
11 | 'How we judge' campaign: carousel and video on the new safeguards | To be appointed (Social Media & Content) | 2027-02-01 | 2027-03-12 | 2027-03-26 | Not started | 0% | 137 | 0% | 0 | GREEN | Source: 10th Edition plan D5.
12 | Regular posting rhythm by content pillar (Instagram 4 posts + 3 Reels a week; Facebook 4-5 a week) | To be appointed (Social Media & Content) | 2027-02-10 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: 10th Edition plan A1 and A3. Running task.
13 | Recruit and vet Media volunteers: photography and video, social media, press | To be appointed (Media Lead) | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file.
14 | Venue reveal content (after the written booking) | To be appointed (Social Media & Content) | 2027-05-03 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Source: 10th Edition plan A3 (venue reveal). Only after the venue is confirmed in writing.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
15 | 'Meet the judges' series (after certificates) | To be appointed (Social Media & Content) | 2027-07-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: 10th Edition plan A4 (day 16).
16 | Photo and video shot list; consent list from Child Welfare; live-stream plan with Technology | To be appointed (Photography & Video) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested.
17 | Program booklet content final and proofread (sponsor list from Partnerships) | To be appointed (Media Lead) | 2027-08-16 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (program printing, originally the last 12 days; moved to September).
18 | Media accreditation: open, review and close | To be appointed (Press & PR) | 2027-09-06 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (media accreditation, originally late Feb).
19 | Sponsor reveals and thank-you posts; finalist spotlights | To be appointed (Social Media & Content) | 2027-09-06 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: 10th Edition plan A3. Suggested timing.
20 | Program, banners and backdrop printed and delivered | To be appointed (Media Lead) | 2027-09-13 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (branding) and D2. Delivered at least 4 weeks before the event.
21 | Media sign-off: every task complete | To be appointed (Media Lead) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
22 | Dry run of the event-day posting and live-stream plan; proofread pre-written posts | To be appointed (Media Lead) | 2027-10-18 | 2027-11-03 | 2027-11-03 | Not started | 0% | 373 | 0% | 0 | GREEN | Review/rehearsal only.
23 | Countdown posts go out from the scheduled queue (no new content) | To be appointed (Social Media & Content) | 2027-10-18 | 2027-11-10 | 2027-11-10 | Not started | 0% | 380 | 0% | 0 | GREEN | Review only. Source: 10th Edition plan A3 (countdown pillar).
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
24 | Event-day live coverage and the press release | To be appointed (Media Lead) | 2027-11-11 | 2027-11-11 | 2027-11-11 | Not started | 0% | 381 | 0% | 0 | GREEN | The date is PROPOSED.
25 | Thank-you posts and photo selection (consented children only) | To be appointed (Social Media & Content) | 2027-11-11 | 2027-11-18 | 2027-12-02 | Not started | 0% | 388 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (within 7 days).
26 | Results article and media follow-up | To be appointed (Press & PR) | 2027-11-12 | 2027-11-26 | 2027-12-10 | Not started | 0% | 396 | 0% | 0 | GREEN | Suggested.
27 | Highlight video and year-end recap | To be appointed (Photography & Video) | 2027-11-15 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Suggested.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Partnerships & Sponsorship
Partnerships & Sponsorship - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Partnerships Lead) |  |  | Tasks | 28 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Submit the Alliance Française Lagos 2027 project (call open Oct 1-31, 2026) | To be appointed | 2026-10-26 | 2026-10-29 | 2026-11-12 | Not started | 0% | 3 | 0% | 0 | GREEN | Source: Funding plan sections 2 and 7. Funder deadline Oct 31, 2026. URGENT: John to name an owner. Confirm the official AF Lagos page first.
2 | Build the sponsor deck: story, nine editions, audience, inclusion, tiers (tier values stay with John) | To be appointed (Partnerships Lead) | 2026-10-29 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 15-45).
3 | Gather editions 1-9 archive facts and impact numbers (verified only) | To be appointed (Partnerships Lead) | 2026-10-29 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 15-45) and section 6 (impact data gap).
4 | Verify past sponsor acknowledgments before reuse (never show them as current sponsors) | To be appointed (Partnerships Lead) | 2026-11-02 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan section 4.
5 | D'Addario eligibility quiz and letter of inquiry (Academy focus; competitions are excluded) | To be appointed (Partnerships Lead) | 2026-11-02 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan sections 3 and 7 (days 15-45).
6 | Send sponsor packs to the top 15 leads | To be appointed (Partnerships Lead) | 2026-11-30 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (early Nov 2026). Moved to after the deck is built. Sponsor letters stay on hold until John says go.
7 | Approach about 25 sponsors (Nestle, MTN Foundation, Access Bank, other banks, FMCG, media) | To be appointed (Partnerships Lead) | 2026-11-30 | 2026-12-28 | 2027-01-11 | Not started | 0% | 63 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 46-75). Letters on hold until John says go.
8 | Register on SAM.gov (needed for U.S. government grants) | To be appointed (Partnerships Lead) | 2026-12-01 | 2026-12-28 | 2027-01-11 | Not started | 0% | 63 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 46-75).
9 | Mockingbird inquiry (only if a U.S. fiscal sponsor is in place; U.S. program only) | To be appointed (Partnerships Lead) | 2026-12-01 | 2027-01-08 | 2027-01-22 | Not started | 0% | 74 | 0% | 0 | GREEN | Source: Funding plan sections 2 and 7. Funder window closes Jan 15, 2027.
10 | Approach the Lagos State Ministry of Education and the Ministry of Tourism, Arts & Culture for endorsement | To be appointed (Partnerships Lead) | 2026-12-01 | 2027-01-29 | 2027-02-12 | Not started | 0% | 95 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (originally early Nov 2026) and section C1.
11 | Follow up and hold sponsor meetings | To be appointed (Partnerships Lead) | 2026-12-29 | 2027-01-12 | 2027-01-26 | Not started | 0% | 78 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 76-90; day 90 = Jan 12, 2027).
12 | Watch for the U.S. Consulate Lagos FY27 call and the British Council 2027 call; line up a UK partner | To be appointed (Partnerships Lead) | 2026-12-29 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 76-90) and section 3.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
13 | Prepare the NAMM Foundation application (Academy; round 1 due about Apr 1, 2027) | To be appointed (Partnerships Lead) | 2027-01-04 | 2027-03-12 | 2027-03-26 | Not started | 0% | 137 | 0% | 0 | GREEN | Source: Funding plan sections 2 and 7. Fits the Academy, not the competition. Re-check the deadline.
14 | Share the proposed date with sponsors and collect responses (feeds the Mar 31 date gate) | To be appointed (Partnerships Lead) | 2027-01-04 | 2027-03-26 | 2027-04-09 | Not started | 0% | 151 | 0% | 0 | GREEN | Suggested.
15 | Recruit and vet Schools Outreach Ambassadors | To be appointed (Partnerships Lead) | 2027-01-11 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Volunteer Roles file.
16 | School outreach: entry guidelines and deadlines | To be appointed (Schools Outreach Ambassador) | 2027-02-01 | 2027-06-18 | 2027-07-02 | Not started | 0% | 235 | 0% | 0 | GREEN | Source: Volunteer Roles file. Registration closes Jun 30, 2027.
17 | Collect letters of support from participating schools | To be appointed (Partnerships Lead) | 2027-03-01 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Funding plan section 8 (documents to prepare).
18 | Headline and gold sponsors secured in writing | To be appointed (Partnerships Lead) | 2027-04-01 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (sponsor contracts, originally Jan 2027). Tier values: John to decide.
19 | In-kind and media partners confirmed (instruments, sound, venue, broadcast) | To be appointed (Partnerships Lead) | 2027-04-05 | 2027-07-30 | 2027-08-13 | Not started | 0% | 277 | 0% | 0 | GREEN | Source: Funding plan section 4 and 10th Edition plan C2.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
20 | Plan sponsor benefits delivery: logo placement on backdrop, program and website | To be appointed (Partnerships Lead) | 2027-07-05 | 2027-08-13 | 2027-08-27 | Not started | 0% | 291 | 0% | 0 | GREEN | Suggested.
21 | All remaining sponsor and partner agreements signed | To be appointed (Partnerships Lead) | 2027-07-05 | 2027-08-31 | 2027-09-14 | Not started | 0% | 309 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (contracts).
22 | Sponsor guests confirmed: seats and protocol, with the Office of the Founder | To be appointed (Partnerships Lead) | 2027-08-02 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Suggested.
23 | Final sponsor and partner list (names and logos) sent to Media | To be appointed (Partnerships Lead) | 2027-08-23 | 2027-09-03 | 2027-09-17 | Not started | 0% | 312 | 0% | 0 | GREEN | Suggested. Media needs it for the program proofread.
24 | Partnerships sign-off: every task complete | To be appointed (Partnerships Lead) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
25 | Contingency plan: sponsor no-show or benefit substitution | To be appointed (Partnerships Lead) | 2027-10-18 | 2027-10-29 | 2027-10-29 | Not started | 0% | 368 | 0% | 0 | GREEN | Contingency only. Suggested.
26 | Sponsor hospitality briefing and sponsor-day rehearsal | To be appointed (Partnerships Lead) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Rehearsal only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
27 | Sponsor thank-you and impact reports | To be appointed (Partnerships Lead) | 2027-11-11 | 2027-11-18 | 2027-12-02 | Not started | 0% | 388 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (within 7 days).
28 | Sponsor renewal conversations for the 11th Edition | To be appointed (Partnerships Lead) | 2027-12-01 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Suggested.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Academy & Education
Academy & Education - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Academy Coordinator) |  |  | Tasks | 17 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Decide the Academic Award practical tests and interactive challenges (two proposals await approval) | John (Founder) | 2026-11-09 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: Practical_Tests_PROPOSAL and Interactive_Challenges_PROPOSAL (not yet approved or published).
2 | Finalize the Academic Award categories (53 kept by John on Oct 23, 2026) and eligibility rules | John (Founder) | 2026-11-09 | 2027-01-15 | 2027-01-29 | Not started | 0% | 81 | 0% | 0 | GREEN | Source: Academic_Award_KEPT file (Student 25, Teacher 11, School 11, Special Needs 6). John's rulings on names and practical tests/challenges still open.
3 | Write the Academic Award scoring models into the rulebook (students, teachers, schools) | To be appointed (Academy Coordinator) | 2026-11-23 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: Jury System plan section 10 (approved as the starting point; reviewed after the first round). The 15% People's Vote is confirmed.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
4 | Publish nomination form and rules; nominations open | To be appointed (Academy Coordinator) | 2027-01-04 | 2027-01-29 | 2027-02-12 | Not started | 0% | 95 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (originally end Jan close; now opens Jan and closes Jun 30).
5 | Nominations open: collect and check nominee records | To be appointed (Academic Awards Assistant) | 2027-01-04 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: 10th Edition plan D2 ('Academic award nominations close'), moved from end Jan 2027 to Jun 30, 2027.
6 | Recruit subject-expert panels (three judges per Academic Award panel) | Chief Judge | 2027-03-01 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Source: Jury System plan section 11.1.
7 | Recruit and vet Music Academy tutor assistants (child-facing) | To be appointed (Academy Coordinator) | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file (Music Academy Tutor Assistant).
8 | Design nominee vote cards with Media and Technology | To be appointed (Academy Coordinator) | 2027-06-01 | 2027-08-13 | 2027-08-27 | Not started | 0% | 291 | 0% | 0 | GREEN | Source: Jury System plan sections 12.1 and Appendix B.
9 | Academy showcase or learning session for schools around the event | To be appointed (Academy Coordinator) | 2027-06-01 | 2027-09-10 | 2027-09-24 | Not started | 0% | 319 | 0% | 0 | GREEN | Suggested. Funders favor year-round Academy work (Funding plan section 1).
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
10 | Verify each shortlisted nominee's records; run practical tests if approved | To be appointed (Academic Awards Assistant) | 2027-07-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Practical_Tests_PROPOSAL (only if John approves).
11 | Award certificates, plaques and trophies: design, spelling check and order | To be appointed (Academic Awards Assistant) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (trophies, plaques, certificates). No costs shown here.
12 | Winner verification process agreed with the independent auditor | To be appointed (Academy Coordinator) | 2027-08-16 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: 10th Edition plan D5.
13 | Academy sign-off: every task complete | To be appointed (Academy Coordinator) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
14 | Check certificate and trophy names against the final finalist lists (spelling only) | To be appointed (Academic Awards Assistant) | 2027-10-18 | 2027-10-29 | 2027-10-29 | Not started | 0% | 368 | 0% | 0 | GREEN | Review only.
15 | Rehearse the Academic Awards ceremony and script | To be appointed (Academy Coordinator) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Rehearsal only.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
16 | Publish Academic Award winners' records and archive them | To be appointed (Academic Awards Assistant) | 2027-11-15 | 2027-12-10 | 2027-12-24 | Not started | 0% | 410 | 0% | 0 | GREEN | Suggested.
17 | Follow-up learning resources for participating schools and teachers | To be appointed (Academy Coordinator) | 2027-12-01 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Suggested.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Finance & Admin
Finance & Admin - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Executive Director (Olubunmi Adebowale) |  |  | Tasks | 21 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Confirm bank account in the organization's name and gather 2-3 years of accounts | Executive Director | 2026-10-26 | 2026-12-04 | 2026-12-18 | Not started | 0% | 39 | 0% | 0 | GREEN | Source: Funding plan section 6 (audited accounts and bank account).
2 | Trustee/board list and governance policies (conflict of interest, finance) | Executive Director | 2026-10-26 | 2026-12-18 | 2027-01-01 | Not started | 0% | 53 | 0% | 0 | GREEN | Source: Funding plan section 6. A conflict-of-interest policy draft is on file (us_nonprofit).
3 | Decide: fiscal sponsor or 501(c)(3) route | John (Founder) | 2026-11-02 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 15-45).
4 | Draft the detailed event budget line by line (the plan estimate is replaced by real quotes later) | Executive Director | 2026-11-02 | 2026-11-27 | 2026-12-11 | Not started | 0% | 32 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 15-45) and 10th Edition plan D6. No figures are shown in this plan.
5 | Start the chosen fiscal-sponsor or 501(c)(3) route | Executive Director | 2026-11-30 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Funding plan section 7; steps in us_nonprofit/501c3_timeline.
6 | Keep a funder calendar and re-check every deadline each month | Executive Director | 2026-11-30 | 2027-06-28 | 2027-07-12 | Not started | 0% | 245 | 0% | 0 | GREEN | Source: Funding plan intro ('re-check every deadline before applying').
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
7 | Set up volunteer records: rota, attendance, ID cards, certificates | To be appointed (Volunteer Coordination Assistant) | 2027-01-11 | 2027-03-05 | 2027-03-19 | Not started | 0% | 130 | 0% | 0 | GREEN | Source: Volunteer Roles file (Volunteer Coordination Assistant).
8 | Gather at least 3 quotes for each major budget line | Executive Director | 2027-01-11 | 2027-04-30 | 2027-05-14 | Not started | 0% | 186 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (at least 3 quotes per major line).
9 | Appoint the independent tabulation auditor (accountant or audit firm) | Executive Director | 2027-02-01 | 2027-04-30 | 2027-05-14 | Not started | 0% | 186 | 0% | 0 | GREEN | Source: 10th Edition plan D5 (pro bono if possible).
10 | Vendor contracts reviewed before signing (venue, sound, printing and others) | Executive Director | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Suggested.
11 | John approves the final event budget | John (Founder) | 2027-05-03 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Suggested.
12 | Funding position report to John: confirmed money versus the gap | Executive Director | 2027-06-14 | 2027-07-02 | 2027-07-16 | Not started | 0% | 249 | 0% | 0 | GREEN | Suggested.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
13 | Vendor payment schedule set so every vendor is secured early | Executive Director | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested. Supports John's early-finish rule.
14 | Event-day volunteer rota built and confirmed; volunteer IDs issued | To be appointed (Volunteer Coordination Assistant) | 2027-08-30 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Source: Volunteer Roles file.
15 | Final funding position report to John | Executive Director | 2027-09-13 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested.
16 | Finance sign-off: every task complete | Executive Director | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
17 | Rehearse the reconciliation check (entries and tickets against the payment system) | Executive Director | 2027-10-18 | 2027-10-29 | 2027-10-29 | Not started | 0% | 368 | 0% | 0 | GREEN | Review/rehearsal only. Suggested.
18 | Final budget-versus-actual review and contingency authority | Executive Director | 2027-11-01 | 2027-11-08 | 2027-11-08 | Not started | 0% | 378 | 0% | 0 | GREEN | Contingency only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
19 | Close the event accounts: reconcile all income and spending | Executive Director | 2027-11-12 | 2027-12-10 | 2027-12-24 | Not started | 0% | 410 | 0% | 0 | GREEN | Suggested.
20 | Impact report (with Programs and Media) | Executive Director | 2027-11-22 | 2028-01-07 | 2028-01-21 | Not started | 0% | 438 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (within 60 days: Jan 10, 2028).
21 | Audited event accounts | Executive Director | 2027-12-13 | 2028-01-07 | 2028-01-21 | Not started | 0% | 438 | 0% | 0 | GREEN | Source: 10th Edition plan D2 (within 60 days: Jan 10, 2028).
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Technology
Technology - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: Lead to be appointed after volunteer assessment (Technology Lead) |  |  | Tasks | 24 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Fix the domain and email so the info@ mailbox is verified | To be appointed (Technology Lead) | 2026-10-26 | 2026-11-13 | 2026-11-27 | Not started | 0% | 18 | 0% | 0 | GREEN | Source: Funding plan section 7 (days 1-14). John to confirm which domain is current.
2 | Load this action plan into the Meeting Room (department sheets, behind-schedule flags, country chat rooms) | To be appointed (Technology Lead) | 2026-11-02 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: Meeting Room plan. Only after John approves the builder prompt. Flagging uses a rule (deadline passed or behind time used), at no cost.
3 | Update the website date wording to match John's decision | To be appointed (Technology Lead) | 2026-11-09 | 2026-12-11 | 2026-12-25 | Not started | 0% | 46 | 0% | 0 | GREEN | Source: DECISIONS_CHECKLIST F17. Waits for the Founder decision.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
4 | Choose the secure sign-in provider (no ChatGPT sign-in) | John (Founder) | 2027-01-04 | 2027-02-26 | 2027-03-12 | Not started | 0% | 123 | 0% | 0 | GREEN | Source: Jury System plan sections 16.3 and 24 ('John and developer').
5 | Online registration standard: one form for all countries, mandatory participant roster and photos | To be appointed (Technology Lead) | 2027-01-04 | 2027-03-26 | 2027-04-09 | Not started | 0% | 151 | 0% | 0 | GREEN | Source: Online Registration Standard draft (not yet approved).
6 | Data protection: privacy notice, access controls for children's data, retention rule | To be appointed (Technology Lead) | 2027-01-04 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Jury System plan section 21. Retention period: John to confirm.
7 | Digital scoring tool: judges score on tablets or a locked form, totals automatic | To be appointed (Technology Lead) | 2027-01-04 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Source: 10th Edition plan D5 and Jury System plan section 16 (development starts Jan 2027).
8 | People's Vote system with anti-fraud checks; choose OTP provider | To be appointed (Technology Lead) | 2027-02-01 | 2027-06-11 | 2027-06-25 | Not started | 0% | 228 | 0% | 0 | GREEN | Source: Jury System plan sections 12 and 24. Vote window and limits: John to confirm.
9 | Admin monitor screen and rule-based flags for judging and votes | To be appointed (Technology Lead) | 2027-03-01 | 2027-06-11 | 2027-06-25 | Not started | 0% | 228 | 0% | 0 | GREEN | Source: Jury System plan sections 17-18.
10 | Secure sign-in live for organizers and remote judges | To be appointed (Technology Lead) | 2027-03-01 | 2027-06-18 | 2027-07-02 | Not started | 0% | 235 | 0% | 0 | GREEN | Source: Jury System plan section 23 (was Jul 2027; moved earlier).
11 | Payment link for entries and tickets (Paystack) - ON HOLD until John says go | To be appointed (Technology Lead) | 2027-04-05 | 2027-06-25 | 2027-07-09 | Not started | 0% | 242 | 0% | 0 | GREEN | On hold per John's standing instruction. Dates are placeholders and shift after the go-ahead. Ticket codes (Event Operations) depend on it.
12 | Recruit and vet Technology volunteers: website, portal, sound/AV and live stream | To be appointed (Technology Lead) | 2027-04-05 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: Volunteer Roles file.
13 | Ticket system: unique code after verified payment; admission recorded to block reuse | To be appointed (Technology Lead) | 2027-04-19 | 2027-07-30 | 2027-08-13 | Not started | 0% | 277 | 0% | 0 | GREEN | Source: NISMCAA website knowledge. Depends on the payment link above.
14 | Confirm sound, lighting, screens and live-stream setup with the venue | To be appointed (Technology Lead) | 2027-06-01 | 2027-08-27 | 2027-09-10 | Not started | 0% | 305 | 0% | 0 | GREEN | Source: 10th Edition plan D6 (stage, sound, lighting, screens; video and live stream).
15 | Security and peak-traffic test of the scoring tool, vote system and website | To be appointed (Technology Lead) | 2027-06-21 | 2027-07-16 | 2027-07-30 | Not started | 0% | 263 | 0% | 0 | GREEN | Suggested. The mock round is in Programs.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
16 | Offline backup: printed score sheets; power and internet backup tested | To be appointed (Technology Lead) | 2027-08-02 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Source: Jury System plan section 15.1 (emergency backup).
17 | Event-day equipment list, device setup, charging and backup hotspots | To be appointed (Technology Lead) | 2027-08-30 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | Suggested.
18 | Feature freeze: from here only fixes | To be appointed (Technology Lead) | 2027-09-01 | 2027-09-15 | 2027-09-29 | Not started | 0% | 324 | 0% | 0 | GREEN | Suggested. Supports John's early-finish rule.
19 | Technology sign-off: every task complete | To be appointed (Technology Lead) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
20 | Code freeze: only emergency fixes; daily health checks | To be appointed (Technology Lead) | 2027-10-15 | 2027-11-10 | 2027-11-10 | Not started | 0% | 380 | 0% | 0 | GREEN | Review only. No new features.
21 | Full technical rehearsal at the venue: sound, projection, stream, scoring on tablets | To be appointed (Technology Lead) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Rehearsal only.
22 | Backup drill: power and internet failure | To be appointed (Technology Lead) | 2027-11-01 | 2027-11-08 | 2027-11-08 | Not started | 0% | 378 | 0% | 0 | GREEN | Contingency only.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
23 | Event-day technology support | To be appointed (Technology Lead) | 2027-11-11 | 2027-11-11 | 2027-11-11 | Not started | 0% | 381 | 0% | 0 | GREEN | The date is PROPOSED.
24 | Back up and archive scoring data, flags and logs | To be appointed (Technology Lead) | 2027-11-15 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Source: Jury System plan section 21.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## International & Diplomacy
International & Diplomacy - 10th Edition action plan
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
Lead: International Legal & Diplomacy Director (Abisadeoluwa A. Adebowale) |  |  | Tasks | 17 | Done | 0 | RED | 0 | AMBER | 0 | Behind: | Nothing behind schedule
Flag rule: RED if the deadline has passed and the task is not done, or 30+ points behind the time used. AMBER 15-29 points. GREEN otherwise. GREY if there is no deadline or the task is on hold. Shaded rows are the final 4 weeks: review, rehearsal and contingency only.
No. | Task | Owner | Start | Deadline (planned finish) | Hard limit (+2 weeks) | Status | % progress | Days left | Time used | Points behind | Flag | Notes
PHASE 1 - FOUNDATIONS: tasks that start Oct 26 - Dec 31, 2026
1 | Decide how to send the letter to the British High Commission Abuja (draft is on file) | Abisade (Legal & Diplomacy Director) | 2026-10-26 | 2026-11-20 | 2026-12-04 | Not started | 0% | 25 | 0% | 0 | GREEN | Source: NISMCAA_Letter_British_High_Commission_Abuja on file; open item about the gov.uk form.
2 | Lawyer review of the global terms of use (brief is ready) | Abisade (Legal & Diplomacy Director) | 2026-11-09 | 2027-02-26 | 2027-03-12 | Not started | 0% | 123 | 0% | 0 | GREEN | Source: legal/lawyer_brief (not legal advice; no lawyer contacted yet). Needs John's go-ahead before anyone is contacted.
3 | Embassy and High Commission outreach list for guests of honor and partners | Abisade (Legal & Diplomacy Director) | 2026-12-01 | 2027-02-26 | 2027-03-12 | Not started | 0% | 123 | 0% | 0 | GREEN | Source: Volunteer Roles file (embassy and partner correspondence). Letters on hold until John says go.
PHASE 2 - BUILD AND RECRUIT: tasks that start Jan 1 - Jun 30, 2027
4 | Decide how each country team takes part in the 10th Edition (guests, online viewing, messages) | Abisade (Legal & Diplomacy Director) | 2027-01-11 | 2027-03-26 | 2027-04-09 | Not started | 0% | 151 | 0% | 0 | GREEN | Suggested.
5 | Recruit and vet the International Relations Assistant | Abisade (Legal & Diplomacy Director) | 2027-01-11 | 2027-03-31 | 2027-04-14 | Not started | 0% | 156 | 0% | 0 | GREEN | Source: Volunteer Roles file (extra checks apply).
6 | Line up a UK partner with the European Coordinator (Samson Orogun) | Abisade (Legal & Diplomacy Director) | 2027-01-11 | 2027-06-30 | 2027-07-14 | Not started | 0% | 247 | 0% | 0 | GREEN | Source: Funding plan section 7 (line up a UK partner) and Volunteer Roles file.
7 | Recruit and vet Country Volunteer Liaisons (each country has its own portal) | Abisade (Legal & Diplomacy Director) | 2027-02-01 | 2027-05-28 | 2027-06-11 | Not started | 0% | 214 | 0% | 0 | GREEN | Source: Volunteer Roles file.
8 | Visa and invitation-letter process for international guests | Abisade (Legal & Diplomacy Director) | 2027-06-01 | 2027-08-13 | 2027-08-27 | Not started | 0% | 291 | 0% | 0 | GREEN | Suggested. Visas can take weeks, so this starts early.
9 | Send invitations to embassies, High Commissions and international partners | Abisade (Legal & Diplomacy Director) | 2027-06-07 | 2027-07-30 | 2027-08-13 | Not started | 0% | 277 | 0% | 0 | GREEN | Suggested.
PHASE 3 - RUN AND PREPARE: tasks that start Jul 1 - Sep 30, 2027 (all finish by Sep 30; hard limit Oct 14)
10 | Protocol plan for diplomats and international guests (with the Office of the Founder) | Abisade (Legal & Diplomacy Director) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested.
11 | Online viewing links for country teams and international supporters (with Technology) | Abisade (Legal & Diplomacy Director) | 2027-08-02 | 2027-09-24 | 2027-10-08 | Not started | 0% | 333 | 0% | 0 | GREEN | Suggested.
12 | International guest attendance confirmed | Abisade (Legal & Diplomacy Director) | 2027-08-30 | 2027-09-17 | 2027-10-01 | Not started | 0% | 326 | 0% | 0 | GREEN | Suggested.
13 | International sign-off: every task complete | Abisade (Legal & Diplomacy Director) | 2027-09-27 | 2027-09-30 | 2027-10-14 | Not started | 0% | 339 | 0% | 0 | GREEN | John's rule: done at least 4 weeks before the event.
PHASE 4 - FINAL 4 WEEKS (Oct 15 - Nov 10, 2027): REVIEW, REHEARSAL AND CONTINGENCY ONLY. NO NEW TASKS.
14 | Brief country liaisons and diplomats; confirm arrivals | Abisade (Legal & Diplomacy Director) | 2027-10-18 | 2027-11-03 | 2027-11-03 | Not started | 0% | 373 | 0% | 0 | GREEN | Review only.
15 | Contingency plan for travel disruption (remote participation) | Abisade (Legal & Diplomacy Director) | 2027-10-25 | 2027-11-05 | 2027-11-05 | Not started | 0% | 375 | 0% | 0 | GREEN | Contingency only. Suggested.
PHASE 5 - EVENT DAY AND AFTER (from Nov 11, 2027)
16 | Thank-you letters to embassies and international partners | Abisade (Legal & Diplomacy Director) | 2027-11-12 | 2027-11-19 | 2027-12-03 | Not started | 0% | 389 | 0% | 0 | GREEN | Suggested.
17 | Share results and highlights with country liaisons; plan next steps per country | Abisade (Legal & Diplomacy Director) | 2027-11-15 | 2027-12-17 | 2027-12-31 | Not started | 0% | 417 | 0% | 0 | GREEN | Suggested.
Formulas:
Hard limit (+2 weeks) = [Deadline (planned finish)]+14
Hard limit (+2 weeks) = [Deadline (planned finish)]
Days left = IF([Deadline (planned finish)]="","",IF([Status]="Done","Done",[Deadline (planned finish)]-TODAY()))
Time used = IF(OR([Start]="",[Deadline (planned finish)]=""),"",IF([Deadline (planned finish)]>[Start],MAX(0,MIN(1,(TODAY()-[Start])/([Deadline (planned finish)]-[Start]))),IF(TODAY()>=[Deadline (planned finish)],1,0)))
Flag = IF(OR([Start]="",[Deadline (planned finish)]=""),"GREY",IF([Status]="On hold","GREY",IF([Status]="Done","GREEN",IF([Deadline (planned finish)]<TODAY(),"RED",IF([Points behind]>=30,"RED",IF([Points behind]>=15,"AMBER","GREEN"))))))

## Read me
READ ME - how this plan works
PROPOSED: Nov 11, 2027 (Thursday). Subject to sponsor approval; may still change. (John, Oct 26, 2026)
John's rule: everything is done EARLY, never at the last minute.
1. All work is planned to finish by Sep 30, 2027 (6 weeks before the event). The hard limit for every task is Oct 14, 2027 (4 weeks before). Hard limit = planned finish + 2 weeks, never later.
2. The last 4 weeks (Oct 15 - Nov 10, 2027) hold review, rehearsal and contingency only. Shaded rows. No new tasks may be added there.
3. 'Deadline' is the planned finish and drives the flags. 'Hard limit' is the safety buffer, not a target.
4. Flag rule (a formula, costs nothing, no AI needed): RED if the deadline has passed and the task is not Done, or if the task is 30+ points behind. AMBER if 15-29 points behind. GREEN otherwise. GREY if there is no deadline or the task is On hold. 'Points behind' = time used minus % progress. 'Time used' = (today - start) / (deadline - start).
5. Update only two columns: Status (Not started, In progress, Done, Blocked, On hold) and % progress. Everything else calculates.
6. If the date changes: change ONE cell, 'All departments' C4. Every date after Mar 31, 2027 is tied to it and moves. Dates before Apr 1, 2027 are fixed calendar dates. Then re-check the 4-week rule and the Mar 31 gate.
7. Today's flags are all GREEN or GREY because nothing has started and no deadline has passed.
Owners
Only known leads are named: John (Founder & President), Abisade (International Legal & Diplomacy Director), the Executive Director (Olubunmi Adebowale), the Project Manager / Secretariat and the Chief Judge (Dr Teemac Omotshola Iseli). Everything else says 'To be appointed' until John appoints department heads after volunteer assessment.
Where a task says 'Suggested' in Notes, it is a standard event-planning step I added; it is not from John's files. Other tasks name their source file and section.
Sources used
NISMCAA_10th_Edition_Plan.docx (sections A, D1-D6); NISMCAA_Volunteer_Roles.md; funding_strategy.md (90-day plan to Jan 12, 2027); NISMCAA_Academy_Launch_Plan_INTERNAL.md; MEETING_ROOM_ACTION_PLAN_FOUND.md; Jury_System_Plan_INTERNAL (sections 10-24); Academic_Award_KEPT_2026-10-23.md; NISMCAA_online_registration_standard.md; legal/lawyer_brief.md; NISMCAA_WEBSITE_KNOWLEDGE (nismcaa_info.txt); DECISIONS_CHECKLIST.md.
No prices, entry or ticket fees, prize amounts, scoring weights or budget figures are in this plan, because they are not final.
Conflicts between sources (how this plan resolved them)
Event date: the 10th Edition plan says Mar 13, 2027. John's message of Oct 26, 2026 and the website say Nov 11, 2027 (proposed). This plan uses Nov 11, 2027, shown as PROPOSED everywhere.
Appeal window: the 10th Edition plan (D5) says 72 hours; the later Jury System plan says 7 days from delivery of each school's report. This plan follows the Jury plan. John to confirm.
Public date wording: John's Oct 15 rule says public pages show only '2027 - Get ready!'. The Nigeria pages say 'proposed Nov 11, 2027'. The ruling is an open decision (first Founder task).
The U.S. Academy event (Nov 21, 2026) and the U.S. program year are separate and are NOT in this plan.
What John must supply
1. An owner for the Alliance Française Lagos submission (the call closes Oct 31, 2026). This is the most urgent item.
2. Names (and emails) for the 7 department heads, the Project Manager, and the Designated Safeguarding Lead.
3. Public wording for the date, and a backup date for the finals.
4. Confirmation of the Mar 31, 2027 sponsor-approval gate, and which venue to pursue.
5. The open Jury plan decisions (criteria weights, penalty ranges, retention period, leaderboard show/hide, vote window, login provider).
6. Approval or changes on the Academic Award practical tests and interactive challenges proposals.
7. The go-ahead for Paystack (on hold), for sponsor letters (on hold) and for contacting a lawyer (not yet contacted).
8. The original numbered Meeting Room action plan, if it differs from this one.
9. Which domain is current for the website and the info@ mailbox.